## MasterConfig
Production URL
Sandbox URL
2nd Sandbox URL
3rd Sandbox URL
SaaS Info URL
SF Ticket Number
New Logo Info
Environment Metadata | Value
Prod Alias
Sandbox Alias
Data Center Location
ProjectPlace Prod Acct #
ProjectPlace Sandbox Acct #
LeanKit Prod ID
LeanKit SB ID
Customer Abbreviation
Prod Server Number
Sandbox Server Number
Customer Current Major Version (Production)
Customer OU Name in AD
New Relic
Unencrypted PVMaster Pass.
Encrypted PVMaster Pass.
AWS Build
Combined Web / App
Environment Logistics | Production | Sandbox
PRM License Count
# Servers
# Web Servers per Environment
Environment Version
Progressing Version |  | .
Latest Release
# of Custom SAS Cubes/Models |  |  | *Detailed List Available Below
Report Migration Required
# of Interfaces |  |  | *Detailed List Available Below
PP Connector
LK Connector
CTM Connector
CTM in use
IP Restrictions
Open Suite
Database Logistics | Production (XXXPROD) | Sandbox (XXXSANDBOX1)
SQL MAX DOP
SQL COST THRESHOLD
DB Encryption
Minimum Server Memory
Maximum Server Memory
DB size
Report Farm URL
Resouce Alignment
| NAME | CPUs | RAM (GB) | HD SIZES | HD IS STANDARD | CUSTOM SCHEDULED TASKS | INSTANCE SIZE (AWS) | AVAILABILITY ZONE (AWS) | IP ADDRESS (AWS) | INSTANCE ID (AWS)
Production Servers
WEB Server
APP Server
CTM Server
SQL Server
SAS Server
PVE Server
Additional Production Web Servers
| NAME | CPUs | RAM (GB) | HD SIZES | HD IS STANDARD | CUSTOM SCHEDULED TASKS | INSTANCE SIZE (AWS) | AVAILABILITY ZONE (AWS) | IP ADDRESS (AWS) | INSTANCE ID (AWS)
Sandbox Servers
WEB Server
APP Server
CTM Server
SQL Server
SAS Server
PVE Server
Additional Sandbox Web Servers
Models
Production
Sandbox
Interfaces
Production
Sandbox
Databases
Production
Details
Sandbox
Details

## Build Data
Inputs for Build (Verify) |  |  |  | Input Calculation Results (Verify)
Description | Value | Description | Value
Build Type |  | Prod Alias
PRM License Count
# Environments Needed
# Servers
# Web Servers per Environment |  | Data Center Location
E1 Build Version |  | Customer Abbreviation
PP Connector Prod Account # |  | Customer OU Name in AD
PP Connector SB Account # |  | New Relic
LK Prod ID # |  | Unencrypted PVMaster Pass.
LK Sandbox ID # |  | Encrypted PVMaster Pass.
Add Non-Standard DB's at build |  | AWS Build
Time Zone
Estimates | Hours
Build Estimate
Secure Server
LK Card Link
SF Ticket Number
Report Farm URL
|  | Notes | Get-ADComputer -Filter 'Name -like "sgpvmXXX*"
Add Non-Standard DB's
Migrate non Prod DB at build
LK Card Info
PVMaster PW
0
Time Zone
0
Maint Day
0
Prod Url
Sandbox Url
Report Url
0
Prod Servers
Sandbox Servers
Note on A4: Chris Tallman: Accessible from explorer, not Sharepoint
Note on E15: Chris Tallman: Accessible from explorer, not Sharepoint

## Jenkins Inputs
| STEP | INPUT | COMPLETE | NOTES | Jenkins Pipe # | Slack Channel Comms
1 | Run All pipe for preprod | https://jenkins.eu.planview.world/job/e1r18_all_pipe/build?delay=0sec | 1 | 1. Run to Deploy update
| TARGET_SERVER_NAME |  |  | 2. Execute DB SQL
| DNS_HOST_NAME |  |  | 3. Complete update, run to postbuild
| CUSTOMER_CODE | 0
| CUSTOMER_NAME | 0
| MAINTENANCE_DAY | 0
| TIME_ZONE | 0
2 | Run All Pipe for PreSandbox | https://jenkins.eu.planview.world/job/e1r18_all_pipe/build?delay=0sec | 1 | 1. Run to Deploy update
| TARGET_SERVER_NAME |  |  | 2. Execute DB SQL
| DNS_HOST_NAME |  |  | 3. Complete update, run to postbuild
| CUSTOMER_CODE | 0
| CUSTOMER_NAME | 0
| MAINTENANCE_DAY | 0
| TIME_ZONE | 0
3 | Run Web Pipe for PRM Web Server in PreProd | https://jenkins.eu.planview.world/job/prm18_web_pipe/build?delay=0sec | 1
TARGET_SERVER_NAME
| DNS_HOST_NAME |  |  | 1.Run to Post Build
| CUSTOMER_CODE | 0
| CUSTOMER_NAME | 0
| MAINTENANCE_DAY | 0
| TIME_ZONE | 0
| PVMASTER_PW | 0
4 | Run Web Pipe for PRM Web Server in PreSandbox | https://jenkins.eu.planview.world/job/prm18_web_pipe/build?delay=0sec | 1
TARGET_SERVER_NAME
| DNS_HOST_NAME |  |  | 1.Run to Post Build
| CUSTOMER_CODE | 0
| CUSTOMER_NAME | 0
| MAINTENANCE_DAY | 0
| TIME_ZONE | 0
| PVMASTER_PW | 0
5 | Run Web Pipe for PRM Web Server in PreProd | https://jenkins.eu.planview.world/job/prm18_web_pipe/build?delay=0sec
TARGET_SERVER_NAME
SAS_SERVER_NAME
SQL_SERVER_NAME
CTM_SERVER_NAME
DNS_HOST_NAME
| CUSTOMER_CODE | 0
| CUSTOMER_NAME | 0
SKIP_NR_AGENT
| MAINTENANCE_DAY | 0
| TIME_ZONE | 0
| PVMASTER_PW | 0
6 | Run Web Pipe for PRM Web Server in PreSandbox | https://jenkins.eu.planview.world/job/prm18_web_pipe/build?delay=0sec
| TARGET_SERVER_NAME |  |  | 2. Continue to Post Build tab below
SAS_SERVER_NAME
CTM_SERVER_NAME
CTM_SERVER_NAME
DNS_HOST_NAME
| CUSTOMER_CODE | 0
| CUSTOMER_NAME | 0
| MAINTENANCE_DAY | 0
| TIME_ZONE | 0
| PVMASTER_PW | 0
7 | Run Web Pipe for PRM Web Server in PreProd | https://jenkins.eu.planview.world/job/prm18_web_pipe/build?delay=0sec
TARGET_SERVER_NAME
SAS_SERVER_NAME
SQL_SERVER_NAME
CTM_SERVER_NAME
DNS_HOST_NAME
| CUSTOMER_CODE | 0
| CUSTOMER_NAME | 0
SKIP_NR_AGENT
| MAINTENANCE_DAY | 0
| TIME_ZONE | 0
| PVMASTER_PW | 0
8 | Run Web Pipe for PRM Web Server in PreSandbox | https://jenkins.eu.planview.world/job/prm18_web_pipe/build?delay=0sec
| TARGET_SERVER_NAME |  |  | 2. Continue to Post Build tab below
SAS_SERVER_NAME
SQL_SERVER_NAME
CTM_SERVER_NAME
DNS_HOST_NAME
| CUSTOMER_CODE | 0
| CUSTOMER_NAME | 0
| MAINTENANCE_DAY | 0
| TIME_ZONE | 0
| PVMASTER_PW | 0
9 | Run Web Pipe for PRM Web Server in PreProd | https://jenkins.eu.planview.world/job/prm18_web_pipe/build?delay=0sec
TARGET_SERVER_NAME
SAS_SERVER_NAME
SQL_SERVER_NAME
CTM_SERVER_NAME
DNS_HOST_NAME
| CUSTOMER_CODE | 0
| CUSTOMER_NAME | 0
SKIP_NR_AGENT
| MAINTENANCE_DAY | 0
| TIME_ZONE | 0
| PVMASTER_PW | 0
10 | Run Web Pipe for PRM Web Server in PreSandbox | https://jenkins.eu.planview.world/job/prm18_web_pipe/build?delay=0sec
TARGET_SERVER_NAME
SAS_SERVER_NAME
SQL_SERVER_NAME
CTM_SERVER_NAME
DNS_HOST_NAME
| CUSTOMER_CODE | 0
| CUSTOMER_NAME | 0
| MAINTENANCE_DAY | 0
| TIME_ZONE | 0
| PVMASTER_PW | 0
11 | Run Web Pipe for PRM Web Server in PreProd | https://jenkins.eu.planview.world/job/prm18_web_pipe/build?delay=0sec
TARGET_SERVER_NAME
SAS_SERVER_NAME
SQL_SERVER_NAME
CTM_SERVER_NAME
| DNS_HOST_NAME | Prod Alias
| CUSTOMER_CODE | Customer Abbreviation
| CUSTOMER_NAME | #REF!
SKIP_NR_AGENT
| MAINTENANCE_DAY | Unencrypted PVMaster Pass.
| TIME_ZONE | Encrypted PVMaster Pass.
12 | Run Web Pipe for PRM Web Server in PreSandbox | https://jenkins.eu.planview.world/job/prm18_web_pipe/build?delay=0sec
| TARGET_SERVER_NAME |  |  | 2. Continue to Checklist tab below
SAS_SERVER_NAME
SQL_SERVER_NAME
CTM_SERVER_NAME
DNS_HOST_NAME
| CUSTOMER_CODE | Customer Abbreviation
| CUSTOMER_NAME | #REF!
| MAINTENANCE_DAY | Unencrypted PVMaster Pass.
| TIME_ZONE | Encrypted PVMaster Pass.

## Post Build
| Objective | NOTES | COMPLETE
1 | Complete Jenkins pipeline to the step 'Ready for post build stuff?' before continuing. | For all servers in all environments
2 | Variables
| $buildServers = | #NAME?
| $buildWebs = | #NAME?
| $buildCtm = | #NAME?
| $buildSqls = | #NAME?
| $key = | "Registry::HKEY_LOCAL_MACHINE\SOFTWARE\WOW6432Node\Microsoft\Windows\CurrentVersion\Uninstall\Planview IT MGUPD"
| $value = | "DisplayName"
3 | Organize AD OU's and Servers | #NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
4 | Create Testing Virtual Directory on web servers.
| From DC Jumpbox | #NAME?
#NAME?
Invoke-Command -ComputerName $prmWebs -ErrorAction Stop -ScriptBlock {Invoke-Expression -Command:"cmd.exe /c 'C:\Deploy\WebserverConfig\FR_TestingWebServerConfig.bat'"}
5 | Run SQL Script | #NAME?
#NAME?
USE PROD
exec sp_change_users_login 'Auto_fix', 'pv_report_user';
exec sp_change_users_login 'Auto_fix', 'ip';
#NAME?
#NAME?
UPDATE ip.tile SET URL = REPLACE(URL, Left(URL, CHARINDEX('/PowerBI', URL) - 1), '') WHERE tile_type = 'PBIX' AND URL NOT LIKE '/PowerBI%';
UPDATE ip.tile SET URL = REPLACE(URL, Left(URL, CHARINDEX('/Reports', URL) - 1), '') WHERE tile_type = 'REPORT' AND URL NOT LIKE '/Reports%';
Update ip.global_options set option_value = 'Y' where option_id = '2245';
update ip.global_options set option_value = 'N' where option_id = '7700';
Update ip.global_options set option_value = '/ng/ctm' where option_id = '2242';
--delete from ip.jobq_fired_triggers
--delete from ip.jobq_paused_trigger_grps;
--delete from ip.jobq_scheduler_state;
--delete from ip.jobq_locks;
--delete from ip.jobq_simple_triggers;
--delete from ip.jobq_simprop_triggers;
--delete from ip.jobq_blob_triggers;
--delete from ip.jobq_cron_triggers;
--delete from ip.jobq_triggers;
--delete from ip.jobq_job_details;
--delete from ip.jobq_calendars;
--delete from ip.job_stream_schedule;
--delete from ip.pv_process_log where logger='Admin.JobStream';
--exec('update ip.planning_entity set [pp_sync] = ''PP`$SyncNo'' where pp_sync in (''PP`$SyncPP'',''PP`$SyncPVE'') ')
USE CONFIG
exec sp_change_users_login 'Auto_fix', 'pv_report_user';
exec sp_change_users_login 'Auto_fix', 'ip';
exec sp_change_users_login 'Auto_fix', 'ro';
#NAME?
USE SANDBOX1
exec sp_change_users_login 'Auto_fix', 'pv_report_user';
exec sp_change_users_login 'Auto_fix', 'ip';
exec sp_change_users_login 'Auto_fix', 'ro';
#NAME?
update ip.global_options set option_value = 'N' where option_id = '7700';
USE SANDBOX2
exec sp_change_users_login 'Auto_fix', 'pv_report_user';
exec sp_change_users_login 'Auto_fix', 'ip';
exec sp_change_users_login 'Auto_fix', 'ro';
#NAME?
update ip.global_options set option_value = 'N' where option_id = '7700';
USE SANDBOX3
exec sp_change_users_login 'Auto_fix', 'pv_report_user';
exec sp_change_users_login 'Auto_fix', 'ip';
exec sp_change_users_login 'Auto_fix', 'ro';
#NAME?
update ip.global_options set option_value = 'N' where option_id = '7700';
USE FASTTRACK
exec sp_change_users_login 'Auto_fix', 'pv_report_user';
exec sp_change_users_login 'Auto_fix', 'ip';
exec sp_change_users_login 'Auto_fix', 'ro';
#NAME?
update ip.global_options set option_value = 'N' where option_id = '7700';
6 | Refresh Olap Properties
7 | Apply Key disk to following databases | Config, SB2, SB3
8 | Update DNS | #NAME?
#NAME?
9 | Delete SQL Temp Files | Invoke-Command -ComputerName $allSql -ScriptBlock {Remove-Item "C:\Program Files\Microsoft SQL Server\MSSQL14.MSSQLSERVER\MSSQL\DATA\temp*.*" -verbose}
10 | Setup DPM
11 | Move VM's to proper cluster
12 | Skip this objective, Encryption not configured
13 | Backup and restore source prod database to target sql server
14 | Migrate Reports | https://jenkins.planviewcloud.net/job/manage_reports_pipe/build?delay=0sec
| CUSTOMER_CODE | 0
| BUILD_SCENARIO | E1_Copy_Same_Farm
| SRC_REPORT_SERVER_URL | FALSE
| SRC_FOLDER | KBL.PVCLOUD.COM
DST_REPORT_SERVER_URL
| DST_FOLDER | .PVCLOUD.COM
15 | Update Datasources
| URL | #NAME?
| Prod Trans Connection String | #NAME?
| Prod DM Connection String | #NAME?
| SB1 Trans Connection String | #NAME?
| SB1 DM Connection String | #NAME?
| PW | hails-nGHrJ
16 | Upload FTA
| URL | https://jenkins.eu.planview.world/job/install_e1_fasttrack/build?delay=0sec
| CR_VERSION | 0
NODE_NAME
17 | Custom Models |  | 1
18 | Custom Cubes |  | 1
19 | Custom scheduled Tasks |  | 1
20 | Custom SQL Jobs |  | 1
21 | Custom web.config values |  | 1
22 | Custom worker processes |  | 1
23 | Restore CTM
24 | CTM Connector
23 | Finish Post Build |  | 1
25 | PRM Adapter - Project Place Connector | https://jenkins.eu.planview.world/job/deploy_prm_adapter/build?delay=0sec
| TARGET_SERVER_FQDN | #NAME?
| DSN | PROD
| CUSTOMER_CODE | 0
| INTHUB_NONPRM_PRODUCT_CODE | pp
| INTHUB_NONPRM_PRODUCT_ENV_ID | projectplace-site-us
| INTHUB_NONPRM_PRODUCT_TENANT_ID | 0
| INTHUB | US (prod.integrations.net)
| PRM Adapter - Project Place Connector | https://jenkins.eu.planview.world/job/deploy_prm_adapter/build?delay=0sec
| TARGET_SERVER_FQDN | #NAME?
| DSN | SANDBOX1
| CUSTOMER_CODE | 0
| INTHUB_NONPRM_PRODUCT_CODE | pp
| INTHUB_NONPRM_PRODUCT_ENV_ID | projectplace-site-us-sb
| INTHUB_NONPRM_PRODUCT_TENANT_ID | 0
| INTHUB | US (prod.integrations.net)
| PRM Adapter - Lean Kit Connector | https://jenkins.eu.planview.world/job/deploy_prm_adapter/build?delay=0sec
| TARGET_SERVER_FQDN | #NAME?
| DSN | PROD
| CUSTOMER_CODE | 0
| INTHUB_NONPRM_PRODUCT_CODE | lk
| INTHUB_NONPRM_PRODUCT_ENV_ID | pd
| INTHUB_NONPRM_PRODUCT_TENANT_ID | 0
| INTHUB | US (prod.integrations.net)
| Rebuild after failure | Rebuild after failure
| PRM Adapter - Lean Kit Connector | https://jenkins.eu.planview.world/job/deploy_prm_adapter/build?delay=0sec
| TARGET_SERVER_FQDN | #NAME?
| DSN | SANDBOX1
| CUSTOMER_CODE | 0
| INTHUB_NONPRM_PRODUCT_CODE | lk
| INTHUB_NONPRM_PRODUCT_ENV_ID | pd
| INTHUB_NONPRM_PRODUCT_TENANT_ID | 0
| INTHUB | US (prod.integrations.net)
| Rebuild after failure | Rebuild after failure
27 | Validation | /planview/login/body.asp?manual=Y |  | 0
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
|  | /planview/login/body.asp?manual=Y |  | 0
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
#NAME?
| Maintenance Day | (Get-ItemProperty -Path $key -Name $value).$value
| Datadog | Get-Service -Name *datadog*
| SSM Agent | Get-Service -Name *Amazon*
| Sumo | Get-Service -Name *sumo*
| SCCM | Get-Service -Name *CcmExec*
| Rapid7 | Get-Service -Name *ir_agent*
| 24x7 | https://www.site24x7.com/sp/client?fs=true#/home
| New Relic | Get-Item "Registry::HKEY_LOCAL_MACHINE\SOFTWARE\New Relic\"
| Load Balancing (F5, AWS) | Verify all web servers are in load balanced pool
OTHER
hails-nGHrJ
Known Build Issues Currently in progress
Edit oData web.config file
| Edit oData web.config file | PveDsn
DPM
| dbconnection.ini | rs_dbpassword="x(!1 {a9"-2Ix{ebmo8Yu,=!M"
Copy dbconection.ini to app servers/additional web servers
trouxAdmin.bat import-config -Dadmin.configs.importFile=f:\baseline\config.xml

## DataRefresh (hidden)
| Objective | NOTES | COMPLETE
1
2
3

## SB Alignment (hidden)
| Objective | NOTES | COMPLETE
1 | Move LK Card | https://planview.leankit.com/board/751178783 Drag or right click LK card Move to Lane -> PRM + CTM under Pre-Prod and Sandbox in the Build Team In Progress column. Assign card to yourself.
1 | Align Server Resources
| Skip this step | Skip this step - No PVE Server | 1
| No Web CPU Alignment Required | No Action Needed
| No Web RAM Alignment Required | No Action Needed
| No Web Disk Alignment Required | No Action Needed
| No App CPU Alignment Required | No Action Needed
| No App RAM Alignment Required | No Action Needed
| No App Disk Alignment Required | No Action Needed
| No SAS CPU Alignment Required | No Action Needed
| No SAS RAM Alignment Required | No Action Needed
| No SAS Disk Alignment Required | No Action Needed
| No SQL CPU Alignment Required | No Action Needed
| No SQL RAM Alignment Required | No Action Needed
| No SQL Disk Alignment Required | No Action Needed
| No SQL MAX DOP Alignment Required | No Action Needed
| No SQL COST THRESHOLD Alignment Required | No Action Needed
| No CTM CPU Alignment Required | No Action Needed
| No CTM RAM Alignment Required | No Action Needed
| No CTM Disk Alignment Required | No Action Needed
2 | Snapshots
VM_GUEST_NAME
SNAPSHOT_NAME
VM_GUEST_NAME
| SNAPSHOT_NAME | Pre_e1r17_SB_Alignment
3 | Take backup of all non system db's in Sandbox
| Run from US Jumpbox, sgcvmrdp02 | #NAME?
#NAME?
cd SQLSERVER:
CD\
#NAME?
(get-item DBBackups.0).start()
(get-item DBBackups.0 ¦ FT CurrentRunStatus)
start-sleep 300
(get-item DBBackups.0 ¦ FT CurrentRunStatus, LastRunOutcome)
F:
#NAME?
4 | Skip this step | Skip this step | 1
5 | #REF! | Enter-PVSession
#REF!
6 | Refresh Olap Properties | Please check Upgrade Data to ensure correct input
SAS_SERVER_NAME
| PVE_VERSION | 18
| CUBE_DATABASE_NAME | #REF!
NODE_NAME_ROPT
7 | Report Copy | https://jenkins.planviewcloud.net/job/manage_reports_pipe/build?delay=0sec
| Jenkins Parameters | 0
.PVCLOUD.COM
.PVCLOUD.COM
8 | Update Reporting Datasources | #REF!
| URL | /Reports/browse/.pvcloud.com/Data%20Sources
| Connection String | #REF!
| Connection String | #REF!
| PW | hails-nGHrJ
9 | Sandbox TSQL post restore | #NAME?
exec sp_change_users_login 'Auto_fix', 'pv_report_user';
exec sp_change_users_login 'Auto_fix', 'ip';
exec sp_change_users_login 'Auto_fix', 'ro';
UPDATE ip.tile SET URL = REPLACE(URL, Left(URL, CHARINDEX('/PowerBI', URL) - 1), '') WHERE tile_type = 'PBIX' AND URL NOT LIKE '/PowerBI%';
UPDATE ip.tile SET URL = REPLACE(URL, Left(URL, CHARINDEX('/Reports', URL) - 1), '') WHERE tile_type = 'REPORT' AND URL NOT LIKE '/Reports%';
Update ip.global_options set option_value = 'Y' where option_id = '2245';
update ip.global_options set option_value = 'N' where option_id = '7700';
Update ip.global_options set option_value = '/ng/ctm' where option_id = '2242';"
#DM Update
#NAME?
#NAME?
exec ip.psp_dm_create_synonyms;
exec ip.psp_dm_create_function;
truncate table ip.dm_dimension_key;
truncate table ip.dm_all_structure_stg;
Truncate table ip.dm_structure_info_int;"
# Running PSP's
exec ip.psp_ppm_cube_pop;
exec ip.psp_ifm_cube;"
11 | #REF! | #REF! | #REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
12 | #REF! | #REF! | #REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
13 | #REF! | #REF! | #REF!
14 | Connectors
| No PRM Adapater | Skip this step
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
16 | Update web.config files
| oData | <add key="PROD" value="$&quot;/7CbH&amp;,[8" />
<add key="CONFIG" value="$&quot;/7CbH&amp;,[8" />
<add key="DMPROD" value="$&quot;/7CbH&amp;,[8" />
| Planview | <add key="PROD" value="User ID=/:(@8HLT[Kfi`r;password=$&quot;/7CbH&amp;,[8" />
<add key="CONFIG" value="User ID=/:(@8HLT[Kfi`r;password=$&quot;/7CbH&amp;,[8" />
<add key="DMPROD" value="User ID=/:(@8HLT[Kfi`r;password=$&quot;/7CbH&amp;,[8" />
17 | Validation
| Validate ADM 01 | /login/body.asp?manual=Y |  | 0
| Validate Versions using following URLs | Start-Process "chrome.exe" "https://.pvcloud.com/planview/diag/version.aspx"
| Test odata with following URLs | Start-Process "chrome.exe" "https://.pvcloud.com/odataservice/OdataService.svc"
| Test Progression Engine | Start-Process "chrome.exe" "https://.pvcloud.com/planview/Progressing/ProgressInteractively.aspx"
| Administration > Reporting > Model Management | Start-Process "chrome.exe" "https://.pvcloud.com/planview/AdminApplication/AdministerOLAPConnStrings.aspx"
| Administration > System Configuration > Database Management | Start-Process "chrome.exe" "https://.pvcloud.com/planview/AdminDatabase/Databases.aspx"
| Administration > Reporting > DataSet Management | Start-Process "chrome.exe" "http://.pvcloud.com/planview/AdminApplication/AdministerDataset.aspx"
| Test Access Manager and Validate TESE is functioning properly | Start-Process "chrome.exe" "https://.pvcloud.com/planview/AdminApplication/AdminServices.aspx"
| Content Search | Start-Process "chrome.exe" "https://.pvcloud.com/planview/AdminApplication/createcontentsearchindex.asp?step=1"
| Validate CTM site launches successfully from PRM | Start-Process "chrome.exe" "https://.pvcloud.com/ng/ctm/"
PRM Health Check
| CTM Health Check | #NAME?
| CTM Health Check | #NAME?
| CTM Health Check | #NAME?
18 | Move LK Card | https://planview.leankit.com/board/751178783 Drag or right click LK card Move to Lane -> Testing -> Sandbox -> 17 Testing and assign to UMT.

## SB Checklist (hidden)
| Objective | NOTES | COMPLETE | COMMENTS
1 | 0 | Drag or right click LK card Move to Lane -> Testing -> Sandbox -> BLD Schedule In-Place.
2 | Customer Notification | https://planview.lightning.force.com/lightning
0
This is a courtesy reminder to inform you that your sandbox environment upgrade will begin today at (using customer local time, specifiy start time here, no need for our start time) and is scheduled for X hours. Please refrain from reporting issues until Planview has notified you that your upgrade is ready. Best Regards, Planview Cloud Operations
3 | Disable Monitoring in Datadog | https://app.datadoghq.com/infrastructure
New-DDDowntime -CustID -Environment Sandbox -Mutelength 5 -Message "Muting environment for In Place Upgrade"
4 | Maintenance Begins
| Reboot all servers to receive Windows updates | #NAME?
Invoke-Command -ComputerName $SbAll -ScriptBlock {Restart-Computer -Force}
| Sleep 5 minutes for reboot | start-sleep 300
| Display maintenance page | #NAME?
Invoke-Command -ComputerName $SBWebs -Command {stop-WebAppPool planview -Verbose}
5 | Disable PRM Services | #NAME?
Invoke-Command -ComputerName $SbPrm -ScriptBlock {Stop-Service -DisplayName Plan* -Verbose; Get-Service -DisplayName Plan* -Verbose}
6 | Backup Databases
#NAME?
cd SQLSERVER:
CD\
#NAME?
(get-item DBBackups.0).start()
(get-item DBBackups.0 ¦ FT CurrentRunStatus)
F:
start-sleep 300
#NAME?
7 | Snapshots
VM_GUEST_NAME
SNAPSHOT_NAME
VM_GUEST_NAME
SNAPSHOT_NAME
VM_GUEST_NAME
SNAPSHOT_NAME
VM_GUEST_NAME
SNAPSHOT_NAME
VM_GUEST_NAME
SNAPSHOT_NAME
No Additional Web Servers
No Additional Web Servers
No Additional Web Servers
No Additional Web Servers
8 | Run SQL CU update Pipe
TARGET_SERVER_NAME
| CU_VERSION | 19
NODE_NAME
9 | Skip this step, no Open Suite |  | 1 | Automated Complete no additional web servers
10 | Run Jenkins CTM Upgrade Pipe
TARGET_SERVER_NAME
DNS_HOST_NAME
| CUSTOMER_CODE | 0
| SKIP_SNAPS | true
NODE_LABEL
11 | Run E1 Upgrade pipe
TARGET_SERVER_NAME
| CUSTOMER_CODE | 0
DNS_HOST_NAME
| SKIP_SNAPS | true
| #REF! | #REF!
12 | Run Jenkins job to upgrade the following additional servers; Web(s)
TARGET_SERVER_NAME
| CUSTOMER_CODE | 0
DNS_HOST_NAME
| SKIP_SNAPS | true
| #REF! | #REF!
|  |  | 1 | Automated Complete no additional web servers
No Additional Web Servers
|  |  | 1 | Automated Complete no additional web servers
No Additional Web Servers
|  |  | 1 | Automated Complete no additional web servers
No Additional Web Servers
1
| No Additional Web Servers |  |  | Automated Complete no additional web servers
13 | Run Jenkins TRX Update pipe
| UPDATE_VERSION | Upgrade Data Version is blank
TARGET_SERVER_NAME
| CUSTOMER_NAME | 0
NODE_LABEL
14 | Run Jenkins E1 Update pipe
| UPDATE_VERSION | Upgrade Data Version is blank
TARGET_SERVER_NAME
| CUSTOMER_CODE | 0
DNS_HOST_NAME
| SKIP_SNAPS | true
| #REF! | #REF!
15 | Run Jenkins job to upgrade the following additional servers; Web(s)
| UPDATE_VERSION | Upgrade Data Version is blank
TARGET_SERVER_NAME
| CUSTOMER_CODE | 0
DNS_HOST_NAME
| SKIP_SNAPS | 0
| #REF! | #REF!
| No Additional Web Servers |  | 1 | Automated Complete no additional web servers
| No Additional Web Servers |  | 1 | Automated Complete no additional web servers
|  |  | 1 | Automated Complete no additional web servers
No Additional Web Servers
| No Additional Web Servers |  | 1 | Automated Complete no additional web servers
16 | Apply key disk to all databases | Key Disk
17 | Flush Akamai | https://control.akamai.com/apps/fast-purge/#/ccu-main
18 | Validation
| Validate ADM 01 | /login/body.asp?manual=Y
| Validate Versions using following URLs | Start-Process "chrome.exe" "https://.pvcloud.com/planview/diag/version.aspx"
| Test odata with following URLs | Start-Process "chrome.exe" "https://.pvcloud.com/odataservice/OdataService.svc"
| Test Progression Engine | Start-Process "chrome.exe" "https://.pvcloud.com/planview/Progressing/ProgressInteractively.aspx"
| Administration > Reporting > Model Management | Start-Process "chrome.exe" "https://.pvcloud.com/planview/AdminApplication/AdministerOLAPConnStrings.aspx"
| Administration > System Configuration > Database Management | Start-Process "chrome.exe" "https://.pvcloud.com/planview/AdminDatabase/Databases.aspx"
| Administration > Reporting > DataSet Management | Start-Process "chrome.exe" "http://.pvcloud.com/planview/AdminApplication/AdministerDataset.aspx"
| Test Access Manager and Validate TESE is functioning properly | Start-Process "chrome.exe" "https://.pvcloud.com/planview/AdminApplication/AdminServices.aspx"
| Content Search | Start-Process "chrome.exe" "https://.pvcloud.com/planview/AdminApplication/createcontentsearchindex.asp?step=1"
| Validate CTM site launches successfully from PRM | Start-Process "chrome.exe" "https://.pvcloud.com/ng/ctm/"
| PRM Health Check | 0
| CTM Health Check | #NAME?
| CTM Health Check | #NAME?
| CTM Health Check | #NAME?
19 | Move LK Card | Drag or right click LK card Move to Lane -> Testing -> Sandbox -> BLD Schedule In-Place and assign to UMT.
20 | Slack UMT | Notify #e1-live-cutovers
@here /login/body.asp?manual=Y is ready for smoke testing

## AWS SB Checklist (hidden)
| STEP | NOTES | COMPLETE | Notes
1 | 0 | Drag or right click LK card Move to Lane -> Testing -> Sandbox -> BLD Schedule In-Place.
2 | Notify customers of outage | This is a courtesy reminder to inform you that your sandbox environment upgrade will begin today at (using customer local time, specifiy start time here, no need for our start time) and is scheduled for X hours. Please refrain from reporting issues until Planview has notified you that your upgraded is ready. Best Regards, Planview Cloud Operations
3 |  | https://app.datadoghq.com/infrastructure
| Disable Monitoring in Datadog (4 hours) | Set-DataDogMaintWin -hosts @('','','','','') -End $(get-date).AddHours(4)
4 | Reboot all servers to receive Windows updates | Restart-Computer -ComputerName , , , -force
5 | Stop Planview services and IIS on all web\app servers | Enter-PSSession -ComputerName .sydney.planviewcloud.net
NET Stop PVAccessManager
NET Stop PlanviewAdminService
NET Stop PVCalendarServer
NET Stop "PlanView Content Management Index Manager"
NET Stop PlanviewEnterpriseScheduler
iisreset /stop
EXIT
Enter-PSSession -ComputerName .sydney.planviewcloud.net
NET Stop PlanviewEnterpriseJobexecution
NET Stop tesegate
EXIT
| No Additional Web Servers | Enter-PSSession -ComputerName .sydney.planviewcloud.net | 1 | Automated Complete no additional web servers
NET Stop PVAccessManager
NET Stop PlanviewAdminService
NET Stop PVCalendarServer
NET Stop "PlanView Content Management Index Manager"
NET Stop PlanviewEnterpriseScheduler
iisreset /stop
EXIT
| No Additional Web Servers | Enter-PSSession -ComputerName .sydney.planviewcloud.net | 1 | Automated Complete no additional web servers
NET Stop PVAccessManager
NET Stop PlanviewAdminService
NET Stop PVCalendarServer
NET Stop "PlanView Content Management Index Manager"
NET Stop PlanviewEnterpriseScheduler
iisreset /stop
EXIT
| No Additional Web Servers | Enter-PSSession -ComputerName .sydney.planviewcloud.net | 1 | Automated Complete no additional web servers
NET Stop PVAccessManager
NET Stop PlanviewAdminService
NET Stop PVCalendarServer
NET Stop "PlanView Content Management Index Manager"
NET Stop PlanviewEnterpriseScheduler
iisreset /stop
EXIT
| No Additional Web Servers | Enter-PSSession -ComputerName .sydney.planviewcloud.net | 1 | Automated Complete no additional web servers
NET Stop PVAccessManager
NET Stop PlanviewAdminService
NET Stop PVCalendarServer
NET Stop "PlanView Content Management Index Manager"
NET Stop PlanviewEnterpriseScheduler
iisreset /stop
EXIT
6 | Take Backup of all databases | DECLARE @name VARCHAR(50) -- database name
DECLARE @path VARCHAR(256) -- path for backup files
DECLARE @fileName VARCHAR(256) -- filename for backup
DECLARE @fileDate VARCHAR(20) -- used for file name
-- specify database backup directory
SET @path = 'F:\SQLBackup\'
-- specify filename format
SELECT @fileDate = CONVERT(VARCHAR(20),GETDATE(),112) + REPLACE(CONVERT(VARCHAR(20),GETDATE(),108),':','')
DECLARE db_cursor CURSOR READ_ONLY FOR
SELECT name
FROM master.dbo.sysdatabases
WHERE name NOT IN ('master','model','msdb','tempdb') -- exclude these databases
OPEN db_cursor
FETCH NEXT FROM db_cursor INTO @name
WHILE @@FETCH_STATUS = 0
BEGIN
SET @fileName = @path + @name + '_' + @fileDate + '.BAK'
BACKUP DATABASE @name TO DISK = @fileName with compression
FETCH NEXT FROM db_cursor INTO @name
END
CLOSE db_cursor
DEALLOCATE db_cursor
7 | Run Jenkins job to create AMI backups; Web(s), App, SQL, CTM | https://jenkins.planviewcloud.net/job/create_ami_pipe/build?delay=0sec
TARGET_SERVER_NAME
| NODE_LABEL | prodswarm
TARGET_SERVER_NAME
| NODE_LABEL | prodswarm
TARGET_SERVER_NAME
| NODE_LABEL | prodswarm
TARGET_SERVER_NAME
| NODE_LABEL | prodswarm
| No Additional Web Servers |  | 1 | Automated Complete no additional web servers
prodswarm
| No Additional Web Servers |  | 1 | Automated Complete no additional web servers
prodswarm
| No Additional Web Servers |  | 1 | Automated Complete no additional web servers
prodswarm
| No Additional Web Servers |  | 1 | Automated Complete no additional web servers
prodswarm
8 | Skip this step, no Open Suite |  | 1 | Automated Check, no additional web servers
9 | UPGRADE E1 | https://jenkins.planviewcloud.net/job/e1_upgrade_pipe/build?delay=0sec
TARGET_SERVER_NAME
| CUSTOMER_CODE | 0
DNS_HOST_NAME
| SKIP_SNAPS | TRUE
| NODE_LABEL | prodswarm
10 | Run Jenkins job to upgrade the following additional servers; Web(s) | https://jenkins.planviewcloud.net/job/e1_upgrade_pipe/build?delay=0sec
TARGET_SERVER_NAME
| CUSTOMER_CODE | 0
DNS_HOST_NAME
| SKIP_SNAPS | TRUE
| NODE_LABEL | prodswarm
TARGET_SERVER_NAME
| CUSTOMER_CODE | 0
DNS_HOST_NAME
SQL_SERVER_NAME
SAS_SERVER_NAME
| SKIP_SNAPS | TRUE
| NODE_LABEL | prodswarm
TARGET_SERVER_NAME
| CUSTOMER_CODE | 0
DNS_HOST_NAME
SQL_SERVER_NAME
SAS_SERVER_NAME
| SKIP_SNAPS | TRUE
| NODE_LABEL | prodswarm
TARGET_SERVER_NAME
| CUSTOMER_CODE | 0
DNS_HOST_NAME
SQL_SERVER_NAME
SAS_SERVER_NAME
| SKIP_SNAPS | TRUE
| NODE_LABEL | prodswarm
TARGET_SERVER_NAME
| CUSTOMER_CODE | 0
DNS_HOST_NAME
SQL_SERVER_NAME
SAS_SERVER_NAME
| SKIP_SNAPS | TRUE
| NODE_LABEL | prodswarm
11 | UPGRADE CTM | https://jenkins.planviewcloud.net/job/ctm_upgrade_pipe/build?delay=0sec
TARGET_SERVER_NAME
DNS_HOST_NAME
| CUSTOMER_CODE | 0
| SKIP_SNAPS | TRUE
| NODE_LABEL | prodswarm
12 | E1 Update | https://jenkins.planviewcloud.net/job/e1_update_pipe/build?delay=0sec
| UPDATE_VERSION | 0
TARGET_SERVER_NAME
| CUSTOMER_CODE | 0
DNS_HOST_NAME
13 | Run Jenkins job to upgrade the following additional servers; Web(s) | https://jenkins.planviewcloud.net/job/e1_update_pipe/build?delay=0sec
| UPDATE_VERSION | 0
TARGET_SERVER_NAME
| CUSTOMER_CODE | 0
DNS_HOST_NAME
| No Additional Web Servers |  | 1 | Automated Complete no additional web servers
| No Additional Web Servers |  | 1 | Automated Complete no additional web servers
| No Additional Web Servers |  | 1 | Automated Complete no additional web servers
| No Additional Web Servers |  | 1 | Automated Complete no additional web servers
14 | TRX Update | https://jenkins.planviewcloud.net/job/trx_update_pipe/build?delay=0sec
TARGET_SERVER_NAME
| CUSTOMER_NAME | 0
| UPDATE_VERSION | 0
| NODE_LABEL | prodswarm
15 | Apply key disk to all databases
16 | Run any patches and DM Generic fix, as necessary
17 | Flush Akamai | https://control.akamai.com/apps/fast-purge/#/ccu-main
18 | 0 | Drag or right click LK card Move to Lane -> Testing -> Sandbox -> 18 Testing and assign to UMT.

## SB Validation (hidden)
| STEP | NOTES | Pass = 2 Warn = 1 Fail = 0 | ISSUES (Link to Slack or Jira)
1 | Validate ADM 01 | /login/body.asp?manual=Y |  |  | 0
2 | Validate Versions using following URLs. | Start-Process "chrome.exe" "https://.pvcloud.com/planview/diag/version.aspx"
3 | Test odata with following URLs | Start-Process "chrome.exe" "https://.pvcloud.com/odataservice/OdataService.svc"
4 | Test Progression Engine | Start-Process "chrome.exe" "https://.pvcloud.com/planview/Progressing/ProgressInteractively.aspx"
5 | Administration > Reporting > Model Management | Start-Process "chrome.exe" "https://.pvcloud.com/planview/AdminApplication/AdministerOLAPConnStrings.aspx"
6 | Administration > System Configuration > Database Management | #REF!
7 | Test Access Manager and Validate TESE is functioning properly | Start-Process "chrome.exe" "https://.pvcloud.com/planview/AdminApplication/AdminServices.aspx"
8 | Verify Generic fix for DM version is at latest | select * from ip.dm_version order by seq desc
9 | Validate CTM site launches successfully from PRM | Start-Process "chrome.exe" "https://.pvcloud.com/ng/ctm/"

## Prod Checklist (hidden)
| Objective | NOTES | COMPLETE | COMMENTS
1 | 0 | Drag or right click LK card Move to Lane -> Scheduled Cutoer -> This Week -> Cutovers -> In Progress
2 | Notify customer that work is beginning | https://planview.lightning.force.com/lightning
0
This is a courtesy reminder to inform you that your production environment upgrade will begin today at (using customer local time, specifiy start time here, no need for our start time) and is scheduled for X hours. Please refrain from reporting issues until Planview has notified you that your upgraded is ready. Best Regards, Planview Cloud Operations
3 | Prior to start time: | https://app.datadoghq.com/infrastructure
| Disable Monitoring in Datadog (4 hours) | New-DDDowntime -CustID Production -Mutelength 5 -Message "Muting environment for In Place Upgrade"
4 | Disable Monitoring in 24x7 | https://www.site24x7.com/app/client#/home/monitors
5 | At designated start time, disable web servers from F5
#NAME?
Invoke-Command -ComputerName $SbAll -ScriptBlock {Restart-Computer -Force}
start-sleep 300
#NAME?
Invoke-Command -ComputerName $SBWebs -Command {stop-WebAppPool planview -Verbose}
6 | Take Backup | #NAME?
cd SQLSERVER:
CD\
#NAME?
(get-item DBBackups.0).start()
(get-item DBBackups.0 ¦ FT CurrentRunStatus)
F:
start-sleep 300
#NAME?
7 | Snapshots
VM_GUEST_NAME
SNAPSHOT_NAME
VM_GUEST_NAME
SNAPSHOT_NAME
VM_GUEST_NAME
SNAPSHOT_NAME
VM_GUEST_NAME
SNAPSHOT_NAME
VM_GUEST_NAME
SNAPSHOT_NAME
No Additional Web Servers
No Additional Web Servers
No Additional Web Servers
No Additional Web Servers
8 | Run SQL CU update Pipe
TARGET_SERVER_NAME
| CU_VERSION | 19
NODE_NAME
9 | Skip this step, no Open Suite |  | 1 | Automated Complete No Open Suite
10 | Run Jenkins CTM Upgrade Pipe
TARGET_SERVER_NAME
DNS_HOST_NAME
| CUSTOMER_CODE | 0
| SKIP_SNAPS | true
11 | Run E1 Upgrade pipe
TARGET_SERVER_NAME
| CUSTOMER_CODE | 0
DNS_HOST_NAME
| SKIP_SNAPS | true
12 | Run Jenkins job to upgrade the following additional servers; Web(s)
TARGET_SERVER_NAME
| CUSTOMER_CODE | 0
DNS_HOST_NAME
| SKIP_SNAPS | true
|  |  | 1 | Automated Complete No additional web servers
No Additional Web Servers
|  |  | 1 | Automated Complete No additional web servers
No Additional Web Servers
|  |  | 1 | Automated Complete No additional web servers
No Additional Web Servers
|  |  | 1 | Automated Complete No additional web servers
No Additional Web Servers
13 | Run Jenkins TRX Update pipe | https://jenkins.us.planview.world/job/trx_update_pipe/build?delay=0sec
| UPDATE_VERSION | 0
TARGET_SERVER_NAME
| CUSTOMER_NAME | 0
NODE_NAME_TUP
14 | Run Jenkins E1 Update pipe
| UPDATE_VERSION | 0
TARGET_SERVER_NAME
| CUSTOMER_CODE | 0
DNS_HOST_NAME
| SKIP_SNAPS | true
15 | Run Jenkins job to upgrade the following additional servers; Web(s) |  |  | FALSE
| UPDATE_VERSION | 0
TARGET_SERVER_NAME
| CUSTOMER_CODE | 0
DNS_HOST_NAME
| SKIP_SNAPS | true
|  |  | 1 | Automated Complete No additional web servers
No Additional Web Servers
|  |  | 1 | Automated Complete No additional web servers
No Additional Web Servers
|  |  | 1 | Automated Complete No additional web servers
No Additional Web Servers
|  |  | 1 | Automated Complete No additional web servers
No Additional Web Servers
16 | Apply key disk to all databases | Key Disk
17 | Flush Akamai | https://control.akamai.com/apps/fast-purge/#/ccu-main
18 | Validation
| Validate ADM 01 | /login/body.asp?manual=Y
| Validate Versions using following URLs | Start-Process "chrome.exe" "https://.pvcloud.com/planview/diag/version.aspx"
| Test odata with following URLs | Start-Process "chrome.exe" "https://.pvcloud.com/odataservice/OdataService.svc"
| Test Progression Engine | Start-Process "chrome.exe" "https://.pvcloud.com/planview/Progressing/ProgressInteractively.aspx"
| Administration > Reporting > Model Management | Start-Process "chrome.exe" "https://.pvcloud.com/planview/AdminApplication/AdministerOLAPConnStrings.aspx"
| Administration > System Configuration > Database Management | Start-Process "chrome.exe" "https://.pvcloud.com/planview/AdminDatabase/Databases.aspx"
| Administration > Reporting > DataSet Management | Start-Process "chrome.exe" "https://.pvcloud.com/planview/AdminApplication/AdministerDataset.aspx"
| Test Access Manager and Validate TESE is functioning properly | Start-Process "chrome.exe" "https://.pvcloud.com/planview/AdminApplication/AdminServices.aspx"
| Content Search | Start-Process "chrome.exe" "https://.pvcloud.com/planview/AdminApplication/createcontentsearchindex.asp?step=1"
| Validate CTM site launches successfully from PRM | Start-Process "chrome.exe" "https://.pvcloud.com/ng/ctm/"
| PRM Health Check | Start-Process "chrome.exe" "https://.pvcloud.com/planview/diag/health.aspx"
| CTM Health Check | Start-Process "chrome.exe" "http:///health"
| CTM Health Check | Start-Process "chrome.exe" "http:///uaa/health"
| CTM Health Check | Start-Process "chrome.exe" "http:///tip/do/health"
19 | Move LK Card | Drag or right click LK card Move to Lane -> Testing -> Sandbox -> BLD Schedule In-Place and assign to UMT.
20 | Slack UMT | Notify #e1-live-cutovers
@here /login/body.asp?manual=Y is ready for smoke testing

## AWS Prod Checklist (hidden)
| STEP | NOTES | COMPLETE | Notes
1 | 0 | Drag or right click LK card Move to Lane -> Scheduled Cutoer -> This Week -> Cutovers -> In Progress
2 | Notify customers of outage | This is a courtesy reminder to inform you that your production environment upgrade will begin today at (using customer local time, specifiy start time here, no need for our start time) and is scheduled for X hours. Please refrain from reporting issues until Planview has notified you that your upgraded is ready. Best Regards, Planview Cloud Operations
3 | Disable 24x7 Monitoring | https://www.site24x7.com/app/client#/home/monitors
4 | Disable Datadog monitoring, Select E1 | https://app.datadoghq.com/infrastructure
Set-DataDogMaintWin -hosts @('','','','') -End $(get-date).AddHours(4)
5 | Restart Servers | Restart-Computer -ComputerName , , , -force
6 | Stop Planview services and IIS on all web\app servers | Enter-PSSession -ComputerName .sydney.planviewcloud.net
NET Stop PVAccessManager
NET Stop PlanviewAdminService
NET Stop PVCalendarServer
NET Stop "PlanView Content Management Index Manager"
NET Stop PlanviewEnterpriseScheduler
iisreset /stop
EXIT
Enter-PSSession -ComputerName .sydney.planviewcloud.net
NET Stop PlanviewEnterpriseJobexecution
NET Stop tesegate
EXIT
| No Additional Web Servers | Enter-PSSession -ComputerName .sydney.planviewcloud.net | 1 | Automated Complete no additional web servers
NET Stop PVAccessManager
NET Stop PlanviewAdminService
NET Stop PVCalendarServer
NET Stop "PlanView Content Management Index Manager"
NET Stop PlanviewEnterpriseScheduler
iisreset /stop
EXIT
| No Additional Web Servers | Enter-PSSession -ComputerName .sydney.planviewcloud.net | 1 | Automated Complete no additional web servers
NET Stop PVAccessManager
NET Stop PlanviewAdminService
NET Stop PVCalendarServer
NET Stop "PlanView Content Management Index Manager"
NET Stop PlanviewEnterpriseScheduler
iisreset /stop
EXIT
| No Additional Web Servers | Enter-PSSession -ComputerName .sydney.planviewcloud.net | 1 | Automated Complete no additional web servers
NET Stop PVAccessManager
NET Stop PlanviewAdminService
NET Stop PVCalendarServer
NET Stop "PlanView Content Management Index Manager"
NET Stop PlanviewEnterpriseScheduler
iisreset /stop
EXIT
| No Additional Web Servers | Enter-PSSession -ComputerName .sydney.planviewcloud.net | 1 | Automated Complete no additional web servers
NET Stop PVAccessManager
NET Stop PlanviewAdminService
NET Stop PVCalendarServer
NET Stop "PlanView Content Management Index Manager"
NET Stop PlanviewEnterpriseScheduler
iisreset /stop
EXIT
7 | Take Backup of all databases | DECLARE @name VARCHAR(50) -- database name
DECLARE @path VARCHAR(256) -- path for backup files
DECLARE @fileName VARCHAR(256) -- filename for backup
DECLARE @fileDate VARCHAR(20) -- used for file name
-- specify database backup directory
SET @path = 'F:\SQLBackup\'
-- specify filename format
SELECT @fileDate = CONVERT(VARCHAR(20),GETDATE(),112) + REPLACE(CONVERT(VARCHAR(20),GETDATE(),108),':','')
DECLARE db_cursor CURSOR READ_ONLY FOR
SELECT name
FROM master.dbo.sysdatabases
WHERE name NOT IN ('master','model','msdb','tempdb') -- exclude these databases
OPEN db_cursor
FETCH NEXT FROM db_cursor INTO @name
WHILE @@FETCH_STATUS = 0
BEGIN
SET @fileName = @path + @name + '_' + @fileDate + '.BAK'
BACKUP DATABASE @name TO DISK = @fileName with compression
FETCH NEXT FROM db_cursor INTO @name
END
CLOSE db_cursor
DEALLOCATE db_cursor
8 | Run Jenkins job to create AMI backups; Web(s), App, SQL, CTM | https://jenkins.planviewcloud.net/job/create_ami_pipe/build?delay=0sec
TARGET_SERVER_NAME
NODE_LABEL
TARGET_SERVER_NAME
| NODE_LABEL | prodswarm
TARGET_SERVER_NAME
| NODE_LABEL | prodswarm
TARGET_SERVER_NAME
| NODE_LABEL | prodswarm
| No Additional Web Servers |  | 1 | Automated Complete no additional web servers
prodswarm
| No Additional Web Servers |  | 1 | Automated Complete no additional web servers
prodswarm
| No Additional Web Servers |  | 1 | Automated Complete no additional web servers
prodswarm
| No Additional Web Servers |  | 1 | Automated Complete no additional web servers
prodswarm
9 | Skip this step, no Open Suite |  | 1 | Automated Complete No Open Suite
10 | Run Jenkins job to upgrade | https://jenkins.planviewcloud.net/job/e1_upgrade_pipe/build?delay=0sec
TARGET_SERVER_NAME
| CUSTOMER_CODE | 0
DNS_HOST_NAME
| SKIP_SNAPS | TRUE
| NODE_LABEL | prodswarm
11 | Run Jenkins job to upgrade the following additional servers; Web(s) | https://jenkins.planviewcloud.net/job/e1_upgrade_pipe/build?delay=0sec |  | Automated Complete no additional web servers
TARGET_SERVER_NAME
| CUSTOMER_CODE | 0
DNS_HOST_NAME
| SKIP_SNAPS | TRUE
| NODE_LABEL | prodswarm
TARGET_SERVER_NAME
| CUSTOMER_CODE | 0
DNS_HOST_NAME
SQL_SERVER_NAME
SAS_SERVER_NAME
| SKIP_SNAPS | TRUE
| NODE_LABEL | prodswarm
TARGET_SERVER_NAME
| CUSTOMER_CODE | 0
DNS_HOST_NAME
SQL_SERVER_NAME
SAS_SERVER_NAME
| SKIP_SNAPS | TRUE
| NODE_LABEL | prodswarm
TARGET_SERVER_NAME
| CUSTOMER_CODE | 0
DNS_HOST_NAME
SQL_SERVER_NAME
SAS_SERVER_NAME
| SKIP_SNAPS | TRUE
| NODE_LABEL | prodswarm
TARGET_SERVER_NAME
| CUSTOMER_CODE | 0
DNS_HOST_NAME
SQL_SERVER_NAME
SAS_SERVER_NAME
| SKIP_SNAPS | TRUE
| NODE_LABEL | prodswarm
12 | Run Jenksin Job to upgrade CTM | https://jenkins.planviewcloud.net/job/ctm_upgrade_pipe/build?delay=0sec
TARGET_SERVER_NAME
DNS_HOST_NAME
| CUSTOMER_CODE | 0
| SKIP_SNAPS | TRUE
| NODE_LABEL | prodswarm
13 | Run Jenkins E1 Update pipe | https://jenkins.planviewcloud.net/job/e1_uppdate_pipe/build?delay=0sec
| UPDATE_VERSION | 0
TARGET_SERVER_NAME
| CUSTOMER_CODE | 0
DNS_HOST_NAME
14 | Run Jenkins job to upgrade the following additional servers; Web(s) | https://jenkins.planviewcloud.net/job/e1_uppdate_pipe/build?delay=0sec
| UPDATE_VERSION | 0
TARGET_SERVER_NAME
| CUSTOMER_CODE | 0
DNS_HOST_NAME
| No Additional Web Servers |  | 1 | Automated Complete no additional web servers
| No Additional Web Servers |  | 1 | Automated Complete no additional web servers
| No Additional Web Servers |  | 1 | Automated Complete no additional web servers
| No Additional Web Servers |  | 1 | Automated Complete no additional web servers
15 | Run Jenkins TRX Update pipe | https://jenkins.planviewcloud.net/job/trx_update_pipe/build?delay=0sec
TARGET_SERVER_NAME
| CUSTOMER_NAME | 0
| UPDATE_VERSION | 0
| NODE_LABEL | prodswarm
16 | Install Latest Progression / Patches
17 | Apply key disk to all databases | Key Disk
18 | Update datamart to laest generic fix to all DM databases
19 | Run progression db script against all db's if not at 06 version.
20 | Flush Akamai | https://control.akamai.com/apps/fast-purge/#/ccu-main
21 | 0 | Drag or right click LK card Move to Lane -> Scheduled Cutoer -> This Week -> Cutovers -> Go Live Testing and assign to UMT

## Prod Validation (hidden)
| STEP | NOTES | Pass = 2 Warn = 1 Fail = 0 | ISSUES (Link to Slack or Jira)
1 | Validate ADM 01 | /login/body.asp?manual=Y |  |  | 0
2 | Validate Versions using following URLs. | Start-Process "chrome.exe" "https://.pvcloud.com/planview/diag/version.aspx"
3 | Test odata with following URLs | Start-Process "chrome.exe" "https://.pvcloud.com/odataservice/OdataService.svc"
4 | Test Progression Engine | Start-Process "chrome.exe" "https://.pvcloud.com/planview/Progressing/ProgressInteractively.aspx"
5 | Administration > Reporting > Model Management | Start-Process "chrome.exe" "https://.pvcloud.com/planview/AdminApplication/AdministerOLAPConnStrings.aspx"
6 | Administration > System Configuration > Database Management | #REF!
7 | Test Access Manager and Validate TESE is functioning properly | Start-Process "chrome.exe" "https://.pvcloud.com/planview/AdminApplication/AdminServices.aspx"
8 | Verify Generic fix for DM version is at latest | select * from ip.dm_version order by seq desc
9 | Validate CTM site launches successfully from PRM | Start-Process "chrome.exe" "https://.pvcloud.com/ng/ctm/"

## Automation
| Command | Params | Values | CALCS
| backup-pvdatabase | -excludedatamart | 0 | 1 | #NAME? | #NAME? | Non AWS Build
| Invoke-Command | -sqlbackupdirectory | 5 | 1 | #NAME? | #NAME? | Non AWS Build
| Set-DataDogMaintWin | -Verbose | 10 |  |  | #NAME? | Non AWS Build
| Invoke-sqlcmd | -hosts | 168 |  |  | #NAME?
| Get-PSDrive | -END | F:\Deploy\UpgradeDBBackup.sql
| Select-Object | get-date | OU=ZZZZ: Decommission Servers,OU=Hosting,DC=us,DC=planview,DC=world |  |  |  | SB All
| Get-ADComputer | .AddHours | F:\sqlbackup |  |  |  | #NAME?
| Get-ChildItem | -QueryTimeout | \\ |  |  |  | #NAME?
| Get-SqlAgent | -ServerInstance | \
| Get-SqlAgentJob | -InputFile | F$ |  |  |  | SB Web
| New-DDDowntime | -ScriptBlock | sqlbackup |  |  |  | #NAME?
| Set-DataDogMaintWin | -CustID | "Muting environment for In Place Upgrade"
| start-sleep | PSComputerName | "
| Invoke-sqlcmd | Move-ADObject |  |  |  |  | Prod All
| Enter-PVSession | -TargetPath | { |  | #NAME? |  | #NAME?
| Get-ADComputer | -Recurse | } |  |  |  | #NAME?
| copy-item | Stop-Service | * |  | #NAME?
| Copy-PVDatabase | Start-Service | @ |  | #NAME? |  | Prod Web
| Start-Process | stop-WebAppPool | (' |  | #NAME?
| Get-Content | -Mutelength | ') |  | #NAME? | #NAME?
| Set-Content | -Message | $ |  | #Non AWS Build
|  | -ComputerName | ','
|  | -Command | ( |  | https://jenkins.eu.planview.world/job/manage_reports_pipe/build?delay=0sec |  | #NAME?
|  | -s | ) |  | https://jenkins.eu.planview.world/job/install_e1_fasttrack/build?delay=0sec |  | #NAME?
|  | -DisplayName | , |  | https://jenkins.eu.planview.world/job/refresh_olap_properties_table/build?delay=0sec
|  | Get-Service | planview |  | https://jenkins.planviewcloud.net/job/manage_reports_pipe/build?delay=0sec
|  | -AWS | 15
|  | Move-ADObject | Plan*
|  | $content = [System.IO.File]::ReadAllText(" | 60
|  | .Replace | frankfurt.planviewcloud.net
|  | [System.IO.File]::WriteAllText(" | Robocopy.exe
|  | $content | -TargetPath "OU=ZZZZ: Decommission Servers,OU=Hosting,DC=us,DC=planview,DC=world" |  | https://control.akamai.com/apps/fast-purge/#/ccu-main
|  | -Path | ¦ |  | https://www.site24x7.com/app/client#/home/monitors
|  | -Destination | F:\Planview\MidTier\webserver\Login\Oauth\web.config |  | https://planview.lightning.force.com/lightning/r/Case/5001M00001Zu5wsQAB/view
|  | -Force | F:\Planview\MidTier\webserver\objects\dbconnection.ini
|  | -SourceDBServer | C:\ProgramData\New Relic\.NET Agent\newrelic.config |  |  |  |  | 0
|  | -SourcePVEServer | F:\baseline\config.xml |  | .sydney.planviewcloud.net
|  | -DestPVEServer | F:\troux\troux_home\18_0_0\utils\admin.properties
|  | -DestDBServer | -sb
|  | -SourceDB | \F$\Planview\MidTier\webserver\objects\dbconnection.ini |  | #NAME?
|  | -DestDB | cd |  | #NAME?
|  | -Cutover | SQLSERVER: |  | #NAME?
|  | (get-item DBBackups.0).start() | SQL\ |  | #NAME?
|  | {(GCI "F:\sqlbackup\" ¦ Measure-Object)} ¦ ft PSComputerName, Count | \Default\JobServer\Jobs |  | #NAME? |  | SQL
|  | (get-item DBBackups.0 ¦ FT | F: |  | #NAME? |  | exec sp_change_users_login 'Auto_fix', 'pv_report_user';
|  | start-WebAppPool | CurrentRunStatus |  | #NAME? |  | exec sp_change_users_login 'Auto_fix', 'ip';
|  | chrome.exe | LastRunOutcome |  | #NAME? |  | exec sp_change_users_login 'Auto_fix', 'ro';
|  | (get-item DBBackups.0).drop() | $Prodservers = |  |  |  | exec ip.psp_ppm_cube_pop;
|  | -ErrorAction | $SQLservers = |  |  |  | exec ip.psp_ifm_cube;
|  | -Environment | $servers = |  |  |  | UPDATE ip.tile SET URL = REPLACE(URL, Left(URL, CHARINDEX('/PowerBI', URL) - 1), '') WHERE tile_type = 'PBIX' AND URL NOT LIKE '/PowerBI%';
|  | Restart-Computer | Start-Transcript -Path F:\temp\ |  |  |  | UPDATE ip.tile SET URL = REPLACE(URL, Left(URL, CHARINDEX('/Reports', URL) - 1), '') WHERE tile_type = 'REPORT' AND URL NOT LIKE '/Reports%';
|  | Backup-SqlDatabase -ServerInstance | \cutover.log |  |  |  | Update ip.global_options set option_value = 'Y' where option_id = '2245';
|  | -Database | Stop-Transcript |  |  |  | update ip.global_options set option_value = 'N' where option_id = '7700';
|  | -BackupFile "\\ | \f$\planview\midtier\webserver\login\SAML\*.config" |  |  |  | Update ip.global_options set option_value = '/ng/ctm' where option_id = '2242';
|  | -query | \f$\planview\midtier\webserver\login\SAML\*.cer" |  |  |  | update ip.ip_user set user_password=' | ' | where user_name='pvmaster';
|  | -Silent | \f$\planview\midtier\webserver\login\SAML\*.pfx"
|  | -Name | /planview/login/body.asp?manual=Y |  | #NAME?
|  | New-ADOrganizationalUnit | /planview/diag/version.aspx |  | #NAME?
|  | -Raw | /odataservice/OdataService.svc |  | #NAME? |  | exec ip.psp_dm_create_synonyms;
|  | -replace | /planview/Progressing/ProgressInteractively.aspx |  | #NAME? |  | exec ip.psp_dm_create_function;
|  |  | /planview/AdminApplication/AdministerOLAPConnStrings.aspx |  | #NAME? |  | truncate table ip.dm_dimension_key;
|  |  | /planview/AdminDatabase/Databases.aspx |  | #NAME? |  | truncate table ip.dm_all_structure_stg;
|  |  | /planview/AdminApplication/AdminServices.aspx |  | #NAME? |  | Truncate table ip.dm_structure_info_int;
|  |  | /ng/ctm/ |  | #NAME?
|  |  | F:\Deploy\ImportConfig.bat |  |  |  | delete from ip.jobq_fired_triggers;
|  |  | Stop |  |  |  | delete from ip.jobq_paused_trigger_grps;
|  |  | {Invoke-Expression -Command:"cmd.exe /c 'F:\ImportConfig.bat'"} |  |  |  | delete from ip.jobq_scheduler_state;
|  |  | Sandbox |  |  |  | delete from ip.jobq_locks;
|  |  | ; |  |  |  | delete from ip.jobq_simple_triggers;
|  |  | = |  |  |  | delete from ip.jobq_simprop_triggers;
|  |  | ' |  |  |  | delete from ip.jobq_blob_triggers;
|  |  | Foreach-Object { $_ -replace "Abbreviation", |  |  |  | delete from ip.jobq_cron_triggers;
|  |  | Foreach-Object { $_ -replace |  |  |  | delete from ip.jobq_triggers;
|  |  | , "Abbreviation" |  |  |  | delete from ip.jobq_job_details;
|  |  | {New-Item -Path F:\SqlBackup\SBSync -ItemType Directory} |  | auprodswarm |  | delete from ip.jobq_calendars;
|  |  | \F$\sqlbackup\SBSync\ |  | frprodswarm |  | delete from ip.job_stream_schedule;
|  |  | _SbSync.bak" |  |  |  | delete from ip.pv_process_log where logger='Admin.JobStream';
|  |  | -CompressionOption On |  |  |  | exec('update ip.planning_entity set [pp_sync] = ''PP`$SyncNo'' where pp_sync in (''PP`$SyncPP'',''PP`$SyncPVE'') ')
Master
ALTER DATABASE
SET SINGLE_USER WITH ROLLBACK IMMEDIATE
DROP DATABASE
RESTORE DATABASE
FROM DISK = 'F:\SQLBackup\SBSync\
|  |  | WITH REPLACE, MOVE 'RPMDEV2' TO 'G:\sqldata\ |  | 0
.mdf',
MOVE 'RPMDEV2_log' TO 'G:\sqldata\
.ldf'"
_SbSync.bak'
CTM*
1
"Muting environment Sandbox Sync"
MOVE 'troux_log' TO 'G:\sqldata\
WITH REPLACE, MOVE 'troux' TO 'G:\sqldata\
|  |  | 1800 |  | https://usreportfarm03.pvcloud.com/Reports
|  |  | /Reports/browse/ |  | https://pbirsfarm01fr.pvcloud.com/Reports
|  |  | /Data%20Sources |  | https://eureportfarm03.pvcloud.com/Reports
|  |  | US |  | https://pbirsfarm03au.pvcloud.com/Reports
EU
Production
|  |  | No |  | 1000
|  |  | Yes |  | 2000
|  |  | F:\ |  | 3500
|  |  | AU_TestingWebServerConfig.bat |  | 5000
|  |  | FR_TestingWebServerConfig.bat |  | 7000
|  |  | C$\ |  | Unlimited
Deploy\
WebserverConfig\
.\add_dns_cname_records.ps1 'sgcvmadc12.us.planview.world' 'pvcloud.com' '
|  |  | ' 'wildcard.pvcloud.com.edgekey.net.' |  | eu-central-1a
|  |  | .us.planview.world |  | eu-central-1b
|  |  | .eu.planview.world |  | eu-central-1c
|  |  | FROM DISK = 'F:\SQLBackup\Build\ |  | ap-southeast-2a
|  |  | _Build.bak' |  | ap-southeast-2b
|  |  | {New-Item -Path F:\SqlBackup\Build -ItemType Directory} |  | ap-southeast-2c
PreSandbox2
PreSandbox3
|  |  | Sandbox 2 |  | projectplace-site-us
|  |  | Sandbox 3 |  | projectplace-site-se
|  |  | OU= |  | projectplace-site-us-sb
projectplace-site-se-sb
PreProd
"
,
XXX
|  |  | {New-Item -Path F:\SqlBackup\PreBuild -ItemType Directory} |  | US (prod.integrations.net)
|  |  | \F$\sqlbackup\PreBuild\ |  | Europe (eu-central-1.pvintegrations.net)
|  |  | _PreBuild.bak' |  | Austrailia (ap-southeast-2.pvintegrations.net)
_preBuild.bak"
/browse/
.pvcloud.com/Data%20Sources
$ProdPrm
$SbPrm
$ProdAll
$SbAll
$ProdWebs
|  |  | $SBWebs | "Registry::HKEY_LOCAL_MACHINE\SOFTWARE\WOW6432Node\Microsoft\Windows\CurrentVersion\Uninstall\Planview IT MGUPD"
|  |  | $allSqls | "DisplayName"
$buildSqls
Data Validation
1
2
3
4
New Logo
PreBuild
Internal
Sandbox 2 Only
Sandbox 3 Only
sg
ln
fr
au
p
t
d
s
q
i
e
| Transactional DB Fixes | fixes orphaned user | exec sp_change_users_login 'Auto_fix', 'pv_report_user';
|  | fixes orphaned user | exec sp_change_users_login 'Auto_fix', 'ip';
|  | fixes orphaned user | exec sp_change_users_login 'Auto_fix', 'ro';
|  | Update tile table removing URL | update ip.ip_user set user_password=' | ' where user_name='pvmaster';
|  | Update tile table removing URL | UPDATE ip.tile SET URL = REPLACE(URL, Left(URL, CHARINDEX('/PowerBI', URL) - 1), '') WHERE tile_type = 'PBIX' AND URL NOT LIKE '/PowerBI%';
|  | Enable CTM | UPDATE ip.tile SET URL = REPLACE(URL, Left(URL, CHARINDEX('/Reports', URL) - 1), '') WHERE tile_type = 'REPORT' AND URL NOT LIKE '/Reports%';
|  | Disables LK Connector | Update ip.global_options set option_value = 'Y' where option_id = '2245';
|  | Defines CTM URL | update ip.global_options set option_value = 'N' where option_id = '7700';
| Manual DB Copy Additional Update | deletes job stream schedules | Update ip.global_options set option_value = '/ng/ctm' where option_id = '2242';
|  | deletes job stream schedules | --delete from ip.jobq_fired_triggers
|  | deletes job stream schedules | --delete from ip.jobq_paused_trigger_grps;
|  | deletes job stream schedules | --delete from ip.jobq_scheduler_state;
|  | deletes job stream schedules | --delete from ip.jobq_locks;
|  | deletes job stream schedules | --delete from ip.jobq_simple_triggers;
|  | deletes job stream schedules | --delete from ip.jobq_simprop_triggers;
|  | deletes job stream schedules | --delete from ip.jobq_blob_triggers;
|  | deletes job stream schedules | --delete from ip.jobq_cron_triggers;
|  | deletes job stream schedules | --delete from ip.jobq_triggers;
|  | deletes job stream schedules | --delete from ip.jobq_job_details;
|  | deletes job stream schedules | --delete from ip.jobq_calendars;
|  | deletes job stream schedules | --delete from ip.job_stream_schedule;
|  | Disables Project Place connector sync | --delete from ip.pv_process_log where logger='Admin.JobStream';
--exec('update ip.planning_entity set [pp_sync] = ''PP`$SyncNo'' where pp_sync in (''PP`$SyncPP'',''PP`$SyncPVE'') ')
Datamart DB Fixes
Sets pdb path for datamart load
|  | update history table | #NAME?
|  | created synonyms for DM load | #NAME?
|  | creates functions | exec ip.psp_dm_create_synonyms;
|  | truncated tables for dm load | exec ip.psp_dm_create_function;
|  | truncated tables for dm load | truncate table ip.dm_dimension_key;
|  | truncated tables for dm load | truncate table ip.dm_all_structure_stg;
Truncate table ip.dm_structure_info_int;"
runs stored procedure for model load
|  | runs stored procedure for model load | exec ip.psp_ppm_cube_pop;
exec ip.psp_ifm_cube;"
Note on C219: Chris Tallman: Production
Note on C220: Chris Tallman: Test
Note on C221: Chris Tallman: Development
Note on C222: Chris Tallman: Sales
Note on C223: Chris Tallman: QE
Note on C224: Chris Tallman: Infrastructure (Not to be used by build team)
Note on C225: Chris Tallman: Development Engineering (Not to be used by build team)

## AutoPop (hidden)
Databases
PROD | PROD |  |  | pvm
CONFIG | CONFIG |  |  | p
SANDBOX1 | SANDBOX1 |  |  | ptvm |  |  |  |  | \\filegateway02\e1-prod- |  | -content-shared\ | .pvcloud.com
SANDBOX2 | SANDBOX2 |  |  | pve
SANDBOX3 | SANDBOX3
CTM | CTM |  | Single Quote
DMPROD |  |  |  | ,
DMSANDBOX1
|  |  | Sandbox Server Names |  | Additional Web Servers
pvmweb01 | pvmwe | pvmweb1 | pvmweb | web | pvmweb01 | pvmapp | pvmsql
pvmweb02 |  | pvmweb2 | pvmapp | app | pvmweb02 | Prod | b1 | pvmpve
pvmweb03 |  | pvmweb3 | pvmsql | sql | pvmweb03
pvmweb04 |  | pvmweb4 | ptvmapp | ctm | pvmweb04
|  |  | pvmsas | sas
2nd Sandbox Server Names
pvmweb01 | pvmwe | pvmweb1 | pvmweb | p | pvmweb01 |  |  |  |  | Data Validation |  |  | Description
pvmweb02 |  | pvmweb2 | pvmapp | app | pvmweb02 |  |  | ppve
pvmweb03 |  | pvmweb3 | pvmsql | sql | pvmweb03 |  |  |  |  | TRUE |  |  | For AWS
pvmweb04 |  | pvmweb4 | ptvmapp | ctm | pvmweb04 |  |  |  |  | FALSE
pvmsas
Upgrade
|  |  | 3nd Sandbox Server Names | [9 empty] | Type
pvmweb01 | pvmwe | pvmweb1 | pvmweb |  | pvmweb01
pvmweb02 |  | pvmweb2 | pvmapp |  | pvmweb02 |  |  | pvmpve
pvmweb03 |  | pvmweb3 | pvmsql |  | pvmweb03 |  |  |  |  | No |  |  | Rebuild
pvmweb04 |  | pvmweb4 | ptvmapp |  | pvmweb04 |  |  |  |  | Yes
pvmsas
[10 empty] | sg |  |  | DataCenter
|  |  | Prod Server Names | [6 empty] | ln
pvmweb01 | pvmwe | pvmweb1 | pvmweb |  | pvmweb01 |  |  | ppve |  | fr
pvmweb02 |  | pvmweb2 | pvmapp |  | pvmweb02 |  |  |  |  | au
pvmweb03 |  | pvmweb3 | pvmsql |  | pvmweb03 |  |  |  |  | rv
pvmweb04 |  | pvmweb4 | ptvmapp |  | pvmweb04
|  |  | pvmsas | [6 empty] | 1000 |  |  | New Relic
1000-2000
2000-3500
SANDBOX | 2nd SANDBOX | 3rd SANDBOX | Prod | [6 empty] | 3500-5000
b1 | b1 | b1 | b1 | [6 empty] | 5000+
b01 | b01 | b01 | b01 | [6 empty] | Unlimited
b2 | b2 | b2 | b2
b02 | b02 | b02 | b02 | [6 empty] | 1SAT |  |  | Maint
b3 | b3 | b3 | b3 |  |  | Set Complex pvmaster password. <PVMasterPass> |  |  |  | 1SUN
b03 | b03 | b03 | b03 |  |  | <add key="PveUserPassword" value="<EncryptedPass>" /> |  |  |  | 2SAT
b4 | b4 | b4 | b4 | [6 empty] | 2SUN
b04 | b04 | b04 | b04 |  |  | \\filegateway02\e1-prod-<DC>-content-shared\\<CustDNS>.pvcloud.com |  |  |  | 3SAT
3SUN
4SAT
4SUN
[10 empty] | 12 or lower |  |  | Current Version
13
|  |  | https:// |  | .pvcloud.com |  |  |  |  | 14
|  |  |  | #VALUE! | -sb.pvcloud.com |  |  |  |  | 15
[5 empty] | -sb2.pvcloud.com |  |  |  |  | 16
[5 empty] | -sb3.pvcloud.com |  |  |  |  | 17
|  |  | Resource Comparison | [6 empty] | https://usreportfarm03.pvcloud.com/ReportServer |  |  | Report Servers
|  |  | Web CPU's | #REF! | [5 empty] | https://eureportfarm03.pvcloud.com/ReportServer
PROD |  |  | Web RAM | #REF! | [5 empty] | https://pbirsfarm03au.pvcloud.com/reportserver
b1 |  |  | Standard Web Disk | #REF! | [5 empty] | https://pbirsfarm01fr.pvcloud.com/reportserver
b01 |  |  | App CPU's
b2 |  |  | App RAM | [6 empty] | None |  |  | Connectors
b02 |  |  | Standard App Disk | [6 empty] | PP
b3 |  |  | SAS CPU | [6 empty] | LK
b03 |  |  | SAS RAM | [6 empty] | CTM
b4 |  |  | Standard SAS Disk
b04 |  |  | SQL CPU | [6 empty] | None |  |  | Interfaces
|  |  | SQL RAM | [6 empty] | 0 - 4
|  |  | Standard CTM Disk | [6 empty] | 5 - 9
Which AWS Environment |  |  | SQL MAX DOP
| 0 | .sydney.planviewcloud.net | SQL COST THRESHOLD
|  |  | CTM CPU's | [6 empty] | 10 +
CTM RAM
Enter Session Powershell | Enter-PSSession -ComputerName |  | Standard CTM Disk | [6 empty] | 0 |  |  | Check Boxes
PROD | Enter-PSSession -ComputerName |  | IP RESTICTIONS | [6 empty] | 1
| Enter-PSSession -ComputerName |  | DB ENCRYPTION | [6 empty] | 2
| Enter-PSSession -ComputerName |  | OPEN SUITE
| Enter-PSSession -ComputerName | [11 empty] | Web Servers
SB | Enter-PSSession -ComputerName |  | Scheduled Task Comparison | [6 empty] | 1
| Enter-PSSession -ComputerName |  | PRM Web | #REF! | [5 empty] | 2
| Enter-PSSession -ComputerName |  | PRM App | #REF! | [5 empty] | 3
| Enter-PSSession -ComputerName |  | SQL | #REF! | [5 empty] | 4
|  |  | CTM | #REF! | [5 empty] | 5
PRM Services
| NET | Start | PVAccessManager | [9 empty] | Jenkins Pipes
|  | Stop | PlanviewAdminService | [6 empty] | https://jenkins.us.planview.world/job/e1_upgrade_pipe/build?delay=0sec
|  |  | PVCalendarServer | [6 empty] | https://jenkins.eu.planview.world/job/e1_upgrade_pipe/build?delay=0sec
|  |  | "PlanView Content Management Index Manager" | [6 empty] | https://jenkins.us.planview.world/job/ctm_upgrade_pipe/build?delay=0sec
|  |  | PlanviewEnterpriseScheduler | [6 empty] | https://jenkins.eu.planview.world/job/ctm_upgrade_pipe/build?delay=0sec
|  |  | PlanviewEnterpriseJobexecution | [6 empty] | https://jenkins.us.planview.world/job/manage_reports_pipe/build?delay=0sec
|  |  | tesegate | [6 empty] | https://jenkins.eu.planview.world/job/manage_reports_pipe/build?delay=0sec |  |  | PRM Web Services
|  |  | PlanviewMessageLoggerDiagnosticService | [6 empty] | https://jenkins.planviewcloud.net/job/manage_reports_pipe/build?delay=0sec
PlanviewPrmAdapterService
PlanviewE1-PRMMonitorMessageLogger
PlanviewE1-PRMPhalkonMessageLogger
iisreset /stop
CTM Services
|  | NET STOP | ctm_uaa
|  | NET START | ctm_gateway
ctm_server
App Services
Kill Tasks
Jenkins Swarm |  |  | taskkill /F /IM
| prodswarm |  | "PlanviewAdminService.exe"
|  |  | "PvsMessageLogger.exe" | [6 empty] | Start-Process "chrome.exe" "https:// | .pvcloud.com/planview/diag/version.aspx"
|  |  | "PrmDiagService.exe" | [6 empty] | Start-Process "chrome.exe" "http:// | .pvcloud.com/odataservice/OdataService.svc"
|  |  | "PrmMonitorService.exe" | [7 empty] | .pvcloud.com/planview/Progressing/ProgressInteractively.aspx"
.pvcloud.com/planview/AdminApplication/AdministerOLAPConnStrings.aspx"
C:\Deploy\StopPRMServices.ps1 | [10 empty] | .pvcloud.com/planview/AdminDatabase/Databases.aspx"
.pvcloud.com/planview/AdminApplication/AdministerDataset.aspx"
|  |  | Mute Data Dog | [7 empty] | .pvcloud.com/planview/AdminApplication/AdminServices.aspx"
|  |  |  | Set-DataDogMaintWin -hosts @(' | ) -End $(get-date).AddHours(4) | [5 empty] | .pvcloud.com/planview/AdminApplication/createcontentsearchindex.asp?step=1"
.pvcloud.com/ng/ctm/"
.pvcloud.com/planview/diag/health.aspx"
/health"
/uaa/health"
|  |  | Latest PRM Patch | [7 empty] | /tip/do/health"
PRM18.0.4WebServerPlatformSetup.exe
Copy Powershell
|  |  |  | copy-item -Path "F:\deploy\StopPRMServices.ps1" -Destination "\\ | \c$\Deploy\" -force -recurse
20.05
Release | 20.04
20.03
20.02
20.01
<add key= | value="$&quot;/7CbH&amp;,[8" />
" | value="User ID=/:(@8HLT[Kfi`r;password=$&quot;/7CbH&amp;,[8" />
| corporate\ushost | iisuser
| eu\euhost | iis
e1-prod-au\sydneyhost
e1-prod-fr\frankfurthost

## Other (hidden)
TAB | DESCRIPTION | AUTOMATION
SB Sync Tab | Restore SB | Enter-PVSession
|  | Copy-PVDatabase -SourcePVEServer |  | -SourceDBServer | -DestPVEServer | -DestDBServer | -SourceDB | PROD | -DestDB | SANDBOX1 | -Verbose -Silent
SB Sync Tab | Tile URL Update | UPDATE ip.tile SET URL = REPLACE(URL, Left(URL, CHARINDEX('/PowerBI', URL) - 1), '') WHERE tile_type = 'PBIX' AND URL NOT LIKE '/PowerBI%';
UPDATE ip.tile SET URL = REPLACE(URL, Left(URL, CHARINDEX('/Reports', URL) - 1), '') WHERE tile_type = 'REPORT' AND URL NOT LIKE '/Reports%';
|  | DB Backup Script | DECLARE @name VARCHAR(50) -- database name
DECLARE @path VARCHAR(256) -- path for backup files
DECLARE @fileName VARCHAR(256) -- filename for backup
DECLARE @fileDate VARCHAR(20) -- used for file name
-- specify database backup directory
SET @path = 'F:\SQLBackup\'
-- specify filename format
SELECT @fileDate = CONVERT(VARCHAR(20),GETDATE(),112) + REPLACE(CONVERT(VARCHAR(20),GETDATE(),108),':','')
DECLARE db_cursor CURSOR READ_ONLY FOR
SELECT name
FROM master.dbo.sysdatabases
WHERE name NOT IN ('master','model','msdb','tempdb') -- exclude these databases
OPEN db_cursor
FETCH NEXT FROM db_cursor INTO @name
WHILE @@FETCH_STATUS = 0
BEGIN
SET @fileName = @path + @name + '_' + @fileDate + '.BAK'
BACKUP DATABASE @name TO DISK = @fileName with compression
FETCH NEXT FROM db_cursor INTO @name
END
CLOSE db_cursor
DEALLOCATE db_cursor
|  | Customer Models | select * from ip.olap_properties where bism_ind ='N'
|  | CTM SQL User Grants | DROP USER | CTM
|  |  | CREATE USER | TIRS
|  |  | ALTER USER | dbo
|  |  | ALTER ROLE | [
|  |  | ADD MEMBER | ]
|  |  | USE | db_datareader
|  |  | GO | db_owner
FOR LOGIN
WITH DEFAULT_SCHEMA=
|  | Connection Sting | Data Source=
Initial Catalog=
;
ReportUserPassword = 'hails-nGHrJ'
& "c:\deploy\Add-ReportUser.ps1" @reportUserCreationParams
PS For Cutover
copy-item -Path "\\techservices\upgrade" -Destination "\\lnpvmBRKweb03\f$\" -Recurse -Force;